## Project Plan and Gantt
Project Name | Traval Vai ERP
Project Manager | Phuong
Project Deliverable
Scope Statement:
Start Date | 2016-05-01
End Date (Phase 1) | 2019-09-30
Overall Progress
UAT URL | http://erp_travalvai.rasia.wiki
Production URL
Sprint | Item Type | Responsible | Start | End | Days | Status
Sprint 1 |  | Phuong | 2016-05-01 | 2016-08-19 | 110 | Completed
Create/Read/Update/Delete (CRUD) Basic Data | Feature |  |  |  |  | Completed
CRUD Costing, Costing Version | Feature |  |  |  |  | Completed
CRUD Price List Factory | Feature |  |  |  |  | Completed
CRUD Price List Zone | Feature |  |  |  |  | Completed
CRUD Price List for Zone (Zone Price) | Feature |  |  |  |  | Completed
CRUD Price List for Agent (Agent Price) | Feature |  |  |  |  | Completed
CRUD Group of Product | Feature |  |  |  |  | Completed
CRUD Type of Product | Feature |  |  |  |  | Completed
CRUD Project | Feature |  |  |  |  | Completed
CRUD Product without calculating Manual Price | Feature |  |  |  |  | Completed
Group of Product-Rearrange description layout | Enhancement |  |  |  |  | Completed
Group of Product-Fill English for empty field | Enhancement |  |  |  |  | Completed
Type of Product-Rearrange description layout | Enhancement |  |  |  |  | Completed
Type of Product-Fill English for empty field | Enhancement |  |  |  |  | Completed
Type of Product-Show Code and Description first | Enhancement |  |  |  |  | Completed
Move ToP and GoP to Product Group | Enhancement |  |  |  |  | Completed
User Screen - Missing the Role field | Bug |  |  |  |  | Completed
Zone - Main Screen - Missing header filters | Bug |  |  |  |  | Completed
Zone - Edit Screen - Error when save information | Bug |  |  |  |  | Completed
Zone-Edit Contact-The fields are empty | Bug |  |  |  |  | Completed
Zone-Create Screen-Error when create contact | Bug |  |  |  |  | Completed
Agent - Main Screen - Missing header filters | Bug |  |  |  |  | Completed
Customer- Main Screen - Missing header filters | Bug |  |  |  |  | Completed
Contacts - Cannot access page | Bug |  |  |  |  | Completed
Customer-Edit Screen-Fields are empty | Bug |  |  |  |  | Completed
Costing List-Main Screen-Put header filters | Bug |  |  |  |  | Completed
Costing List-Ask for confirmation before delete | Bug |  |  |  |  | Completed
Costing Version-Show English description | Bug |  |  |  |  | Completed
Project-Main Screen-Adjust column width | Bug |  |  |  |  | Completed
Project-Main Screen- Filter ACTIONS doesn't work | Bug |  |  |  |  | Completed
Project-Create Screen-Save button doesn't work | Bug |  |  |  |  | Completed
Sprint 2 |  | Phuong | 2016-08-22 | 2016-09-01 | 10 | Completed
CRUD Contract | Feature |  |  |  |  | Completed
Create Product with calculating Manual Price | Feature |  |  |  |  | Completed
Project-Create Screen-Project number has to be consecutive | Bug |  |  |  |  | Completed
Project-Main Screen-Add selection of lines selector | Enhancement |  |  |  |  | Completed
Project-Create Screen-Customer field lacks of Filter | Enhancement |  |  |  |  | Completed
Project-Edit Screen-Show Zone and Agent decription | Enhancement |  |  |  |  | Completed
Project-Edit Screen-Close window after saving | Enhancement |  |  |  |  | Completed
Sprint 3 |  | Phuong | 2016-09-05 | 2016-09-16 | 11 | In Progress
Project-Edit Screen-Enhance Comment feature | Enhancement
Product - Apply Contract into Product's Price calculation | Enhancement
Price List Factory - Create by Copy | Enhancement
Price List Zone - Create by Copy | Enhancement
Order - View Order Detail | Feature
Order - Create new Order | Feature
Launch |  |  | 2016-09-29 | 2016-09-30 | 1