## Weekly Status - 20160923
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE
From Report Date: | 2016-09-12 |  | Schedule | GOOD | Schedule to complete Phase 1
Report Date: | 2016-09-23 |  | Resource | NOT GOOD | Loc (the most experienced developer) left.
Complete By (Milestone): | Phase 1
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Fixbug - Type of Product | DONE | 2016-09-23 | Don | Dan
02 | Fixbug - Group of Product | DONE | 2016-09-23 | Thinh | Dan
03 | Enhance- Costing - Create by Copy | DONE | 2016-09-23 | Thinh | Dan
04 | Enhance - P.L. Factory - Main List | DONE | 2016-09-23 | Thinh | Dan
05 | Enhance - P.L. Factory - Create new P.L. | DONE | 2016-09-23 | Thinh | Dan
06 | Enhance - P.L. Zone - Main List | DONE | 2016-09-23 | Don | Dan
07 | Enhance - P.L. Zone - Create new P.L. | DONE | 2016-09-23 | Don | Dan
08 | Enhance - Product - Create new Product | DONE | 2016-09-23 | Thinh | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
02 | Training - Introduce AngularJS to An | Done |  | Phuong
03 | Training - Introduce ERP Project to An | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | P.L. Factory - Create by Copy | 2016-09-26 | Thinh
02 | P.L. Zone - Create by Copy | 2016-09-26 | Don
03 | Pattern - Enhance Main Screen | 2016-09-30 | Don
04 | Pattern - Enhance Detail Screen | 2016-09-30 | Don
05 | Pattern - Enhance Pattern's Part | 2016-09-30 | Don
06 | Pattern - Enhance Pattern's Variation | 2016-09-30 | Thinh
07 | Pattern - Enhance Pattern's Comment | 2016-09-30 | Thinh
08 | Project - Enhance Project's Comment | 2016-09-30 | Thinh
09 | Admin - Fixbug Edit Agent, Zone, Customer | 2016-09-30 | An

## Milestones
Index | Milestone | Due Date | Items
1 | Phase 1 | 2016-09-30 | 1. Admin 2 Costing 3. Price List Factory 4 Price List Zone 5. Project 6. Product
2 | Phase 2 | 2016-10-31 | 1. Order 2. Shipment