## Weekly Status - 20161015
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE | There are some silly bugs
From Report Date: | 2016-10-10 |  | Schedule | GOOD
Report Date: | 2016-10-14 |  | Resource | GOOD
Complete By (Milestone): | Phase 2
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Enhance - Pattern - Pattern List - Image proportion | DONE | 2016-10-14 | Thinh | Phuong
02 | Enhance - Pattern - Pattern Parts - Rearrange UI | DONE | 2016-10-14 | Don | Phuong
03 | Enhance - Pattern - Pattern Variation - Rearrange the UI | DONE | 2016-10-14 | Don | Phuong
05 | Fix bug - Product and Contract | DONE | 2016-10-14 | An | Phuong
06 | Fix bug - Costing | DONE | 2016-10-14 | Don | Phuong
07 | Feature - Order - Back-end service to add new Order | DONE | 2016-10-14 | Thinh | Phuong
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
01 | Training - Git to An and Loan | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | Feature - Order - Add New Order by Size quantity | 2016-10-21 | Thinh & Don
02 | Feature - Order - Add New Order by Size, Number and Name - Manually Add | 2016-10-21 | Thinh & Don
03 | Feature - Order -Add New Order - View Order Detail | 2016-10-21 | Thinh & Don
04 | Enhance - Admin, Product, Price List, Costing, Project, Pattern | 2016-10-21 | Thinh, Don & An

## Weekly Status - 20161007
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE | There are some silly bugs
From Report Date: | 2016-10-03 |  | Schedule | GOOD
Report Date: | 2016-10-07 |  | Resource | GOOD
Complete By (Milestone): | Phase 2
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Feature - Pattern - Pattern Comment - View Comment Detail and Edit Comment | DONE | 2016-10-07 | Thinh | Dan
02 | Feature - Pattern - Enhance Pattern Variation | DONE | 2016-10-07 | Don | Dan
03 | Enhance - Customer - Allow Factory and Zone to create Customer | DONE | 2016-10-07 | Don | Dan
05 | Admin - Enhance Zone Price, Agent Price | DONE | 2016-10-07 | An | Dan
06 | Feature – View full size image when clicking on thumbnail image | DONE | 2016-10-07 | Don | Dan
07 | Enhance - User - Remove constraint when removing a user | DONE | 2016-10-07 | Thinh | Dan
08 | Enhance - Product - Change the procedure to add new Product | DONE | 2016-10-07 | Thinh | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
01 | Training - AngularJS to An and Loan | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | Feature - Order - Add New Order by Size quantity | 2016-10-14 |  | PiC will be assigned in kick-off Sprint meeting
02 | Feature - Order - Add New Order by Size, Number and Name - Manually Add | 2016-10-14 |  | PiC will be assigned in kick-off Sprint meeting
03 | Feature - Order -Add New Order - View Order Detail | 2016-10-14 |  | PiC will be assigned in kick-off Sprint meeting

## Weekly Status - 20160930
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE
From Report Date: | 2016-09-26 |  | Schedule | AVERAGE | Have not completed all features related to Pattern (Variation, Comment (View Detail, Edit Comment)) yet
Report Date: | 2016-09-30 |  | Resource | GOOD
Complete By (Milestone): | Phase 1
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Fixbug - Costing - Create by Copy - Type of Product option | DONE | 2016-09-30 | Thinh | Dan
02 | Feature - P.L. Factory - Create by Copy | DONE | 2016-09-30 | Thinh | Dan
03 | Feature - P.L. Zone - Create by Copy | DONE | 2016-09-30 | Don | Dan
04 | Feature -Project - Project Comment | DONE | 2016-09-30 | Don | Dan
05 | Feature - Pattern - Pattern List | DONE | 2016-09-30 | Thinh | Dan
06 | Feature - Pattern - Pattern Part | DONE | 2016-09-30 | Don | Dan
07 | Feature - Pattern - Pattern Comment - Add Comment | DONE | 2016-09-30 | Thinh | Dan
08 | Admin - Enhance Edit/Add Agent, Zone, Customer | DONE | 2016-09-30 | An | Dan
09 | Feature - Product - Add Product | DONE | 2016-09-31 | Thinh | Dan
10 | Feature – View full size image when clicking on thumbnail image | DONE | 2016-09-32 | Don | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | Feature - Pattern - Pattern Comment - View Comment Detail and Edit Comment | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
02 | Feature - Pattern - Enhance Pattern Variation | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
03 | Feature - Order - Add New Order by Size quantity | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
04 | Feature - Order - Add New Order by Size, Number and Name - Manually Add | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
05 | Feature - Order - Add New Order by Size, Number and Name - Import from Excel | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
06 | Feature - Order -Add New Order - View Order Detail | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
09 | Admin - Enhance Zone Price, Agent Price | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting

## Weekly Status - 20160923
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE
From Report Date: | 2016-09-12 |  | Schedule | GOOD | Schedule to complete Phase 1
Report Date: | 2016-09-23 |  | Resource | NOT GOOD
Complete By (Milestone): | Phase 1
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Fixbug - Type of Product | DONE | 2016-09-23 | Don | Dan
02 | Fixbug - Group of Product | DONE | 2016-09-23 | Thinh | Dan
03 | Enhance- Costing - Create by Copy | DONE | 2016-09-23 | Thinh | Dan
04 | Enhance - P.L. Factory - Main List | DONE | 2016-09-23 | Thinh | Dan
05 | Enhance - P.L. Factory - Create new P.L. | DONE | 2016-09-23 | Thinh | Dan
06 | Enhance - P.L. Zone - Main List | DONE | 2016-09-23 | Don | Dan
07 | Enhance - P.L. Zone - Create new P.L. | DONE | 2016-09-23 | Don | Dan
08 | Enhance - Product - Create new Product | DONE | 2016-09-23 | Thinh | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
01 | Training - Introduce AngularJS to An | Done |  | Phuong
02 | Training - Introduce ERP Project to An | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | P.L. Factory - Create by Copy | 2016-09-26 | Thinh
02 | P.L. Zone - Create by Copy | 2016-09-26 | Don
03 | Pattern - Enhance Main Screen | 2016-09-30 | Don
04 | Pattern - Enhance Detail Screen | 2016-09-30 | Don
05 | Pattern - Enhance Pattern's Part | 2016-09-30 | Don
06 | Pattern - Enhance Pattern's Variation | 2016-09-30 | Thinh
07 | Pattern - Enhance Pattern's Comment | 2016-09-30 | Thinh
08 | Project - Enhance Project's Comment | 2016-09-30 | Thinh
09 | Admin - Fixbug Edit Agent, Zone, Customer | 2016-09-30 | An

## Milestones
Index | Milestone | Due Date | Items
1 | Phase 1 | 2016-09-30 | 1. Admin 2 Costing 3. Price List Factory 4 Price List Zone 5. Project 6. Product
2 | Phase 2 | 2016-10-31 | 1. Order 2. Shipment