## User Story Timeline
User Story Timeline
Time for 1 User Story | 16 | Hours
Task | Percentage | Hour
Requirement | 25% | 4
Design | 2% | 0.32
Coding & Unit test | 60% | 9.6
Test | 10% | 1.6
Deployment & CM & Support User Acceptant Test | 1% | 0.16
Project Management | 2% | 0.32

## Weekly Status - 20161111
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | GOOD
Application ID/Name: | NA |  | Quality | GOOD
From Report Date: | 2016-10-31 |  | Schedule | GOOD
Report Date: | 2016-11-11 |  | Resource | GOOD
Complete By (Milestone): | Phase 3
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Order List - Export to Excel | DONE | 2016-11-11 | An | Dan
02 | Order List - Export to PDF | DONE | 2016-11-11 | An | Dan
03 | Order List - Delete Order | DONE | 2016-11-11 | Thinh | Dan
04 | Order Detail - Exhance Procedure to add Product | DONE | 2016-11-11 | Thinh | Dan
05 | Order Detail - Edit Product Quantity - By Size | DONE | 2016-11-11 | Thinh | Dan
06 | Order Detail - Edit Product Quantity - By Name and Number | DONE | 2016-11-11 | Thinh | Dan
07 | Order Detail - Delete Product | DONE |  | Thinh | Dan
08 | Order Detail - Export to Excel | DONE |  | An | Dan
09 | Order Detail - Export to PDF | DONE |  | An | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment | User Stories
01 | Shipment - Basic Data - Freight |  |  |  | 2
02 | Shipment - Basic Data - Forwarder |  |  |  | 2
03 | Shipment - Basic Data - Incoterm |  |  |  | 2
04 | Shipment - Basic Data - Shipment Type |  |  |  | 2
05 | Shipment - Basic Data - Type of Box |  |  |  | 2
|  |  |  | Total | 10

## Weekly Status - 20161028
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE
From Report Date: | 2016-10-17 |  | Schedule | LATE | There a some minor functions have not been completed yet
Report Date: | 2016-10-28 |  | Resource | GOOD
Complete By (Milestone): | Phase 2
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Order - Order List – Lines View and Resume View (all levels | DONE | 2016-10-28 | Thinh | Dan
02 | Order - Creating Order (all levels) | DONE | 2016-10-28 | Don | Dan
03 | Order - Order Detail – Line View and Size View (all levels) | DONE | 2016-10-28 | Thinh | Dan
05 | Order - Adding Product to Order (all levels) | DONE | 2016-10-28 | Don | Dan
06 | Adming - Currency Convert - Service to update exchange rate | DONE | 2016-10-28 | Phuong | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | 1. PAGE ACCESS - Page access according to user’s role | 2016-11-04
02 | 2. MESSAGE TRANSLATION | 2016-11-04
03 | 3. DATA GRID - Support shortcut key | 2016-11-04
04 | 4. DATA GRID - Correct name of column’s header | 2016-11-04
05 | 5. DATA GRID - Adjust column’s width | 2016-11-04
06 | 6. DATA GRID - Define printed form | 2016-11-04
07 | 7. UPDATING DATA - Just allow 1 user update a specific record at 1 time | 2016-11-04
08 | 8. Shipment | 2016-11-04

## Weekly Status - 20161015
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE | There are some silly bugs
From Report Date: | 2016-10-10 |  | Schedule | GOOD
Report Date: | 2016-10-14 |  | Resource | GOOD
Complete By (Milestone): | Phase 2
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Enhance - Pattern - Pattern List - Image proportion | DONE | 2016-10-14 | Thinh | Phuong
02 | Enhance - Pattern - Pattern Parts - Rearrange UI | DONE | 2016-10-14 | Don | Phuong
03 | Enhance - Pattern - Pattern Variation - Rearrange the UI | DONE | 2016-10-14 | Don | Phuong
05 | Fix bug - Product and Contract | DONE | 2016-10-14 | An | Phuong
06 | Fix bug - Costing | DONE | 2016-10-14 | Don | Phuong
07 | Feature - Order - Back-end service to add new Order | DONE | 2016-10-14 | Thinh | Phuong
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
01 | Training - Git to An and Loan | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | Feature - Order - Add New Order by Size quantity | 2016-10-21 | Thinh & Don
02 | Feature - Order - Add New Order by Size, Number and Name - Manually Add | 2016-10-21 | Thinh & Don
03 | Feature - Order -Add New Order - View Order Detail | 2016-10-21 | Thinh & Don
04 | Enhance - Admin, Product, Price List, Costing, Project, Pattern | 2016-10-21 | Thinh, Don & An

## Weekly Status - 20161007
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE | There are some silly bugs
From Report Date: | 2016-10-03 |  | Schedule | GOOD
Report Date: | 2016-10-07 |  | Resource | GOOD
Complete By (Milestone): | Phase 2
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Feature - Pattern - Pattern Comment - View Comment Detail and Edit Comment | DONE | 2016-10-07 | Thinh | Dan
02 | Feature - Pattern - Enhance Pattern Variation | DONE | 2016-10-07 | Don | Dan
03 | Enhance - Customer - Allow Factory and Zone to create Customer | DONE | 2016-10-07 | Don | Dan
05 | Admin - Enhance Zone Price, Agent Price | DONE | 2016-10-07 | An | Dan
06 | Feature – View full size image when clicking on thumbnail image | DONE | 2016-10-07 | Don | Dan
07 | Enhance - User - Remove constraint when removing a user | DONE | 2016-10-07 | Thinh | Dan
08 | Enhance - Product - Change the procedure to add new Product | DONE | 2016-10-07 | Thinh | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
01 | Training - AngularJS to An and Loan | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | Feature - Order - Add New Order by Size quantity | 2016-10-14 |  | PiC will be assigned in kick-off Sprint meeting
02 | Feature - Order - Add New Order by Size, Number and Name - Manually Add | 2016-10-14 |  | PiC will be assigned in kick-off Sprint meeting
03 | Feature - Order -Add New Order - View Order Detail | 2016-10-14 |  | PiC will be assigned in kick-off Sprint meeting

## Weekly Status - 20160930
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE
From Report Date: | 2016-09-26 |  | Schedule | AVERAGE | Have not completed all features related to Pattern (Variation, Comment (View Detail, Edit Comment)) yet
Report Date: | 2016-09-30 |  | Resource | GOOD
Complete By (Milestone): | Phase 1
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Fixbug - Costing - Create by Copy - Type of Product option | DONE | 2016-09-30 | Thinh | Dan
02 | Feature - P.L. Factory - Create by Copy | DONE | 2016-09-30 | Thinh | Dan
03 | Feature - P.L. Zone - Create by Copy | DONE | 2016-09-30 | Don | Dan
04 | Feature -Project - Project Comment | DONE | 2016-09-30 | Don | Dan
05 | Feature - Pattern - Pattern List | DONE | 2016-09-30 | Thinh | Dan
06 | Feature - Pattern - Pattern Part | DONE | 2016-09-30 | Don | Dan
07 | Feature - Pattern - Pattern Comment - Add Comment | DONE | 2016-09-30 | Thinh | Dan
08 | Admin - Enhance Edit/Add Agent, Zone, Customer | DONE | 2016-09-30 | An | Dan
09 | Feature - Product - Add Product | DONE | 2016-09-31 | Thinh | Dan
10 | Feature – View full size image when clicking on thumbnail image | DONE | 2016-09-32 | Don | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | Feature - Pattern - Pattern Comment - View Comment Detail and Edit Comment | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
02 | Feature - Pattern - Enhance Pattern Variation | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
03 | Feature - Order - Add New Order by Size quantity | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
04 | Feature - Order - Add New Order by Size, Number and Name - Manually Add | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
05 | Feature - Order - Add New Order by Size, Number and Name - Import from Excel | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
06 | Feature - Order -Add New Order - View Order Detail | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting
09 | Admin - Enhance Zone Price, Agent Price | 2016-10-07 |  | PiC will be assigned in kick-off Sprint meeting

## Weekly Status - 20160923
Weekly Status Report
Production Department
Project Name: | Travalvai_ERP |  | SUMMARY
Project ID: | NA |  | TOTAL STATUS | AVERAGE
Application ID/Name: | NA |  | Quality | AVERAGE
From Report Date: | 2016-09-12 |  | Schedule | GOOD | Schedule to complete Phase 1
Report Date: | 2016-09-23 |  | Resource | NOT GOOD
Complete By (Milestone): | Phase 1
Project Manager: | Phuong
Reporter | Phuong
PLANNED THIS SPRINT
TASK # | Description | Status | Due Date | Developer | Responsible Tester | Developer Comment | Feedback
01 | Fixbug - Type of Product | DONE | 2016-09-23 | Don | Dan
02 | Fixbug - Group of Product | DONE | 2016-09-23 | Thinh | Dan
03 | Enhance- Costing - Create by Copy | DONE | 2016-09-23 | Thinh | Dan
04 | Enhance - P.L. Factory - Main List | DONE | 2016-09-23 | Thinh | Dan
05 | Enhance - P.L. Factory - Create new P.L. | DONE | 2016-09-23 | Thinh | Dan
06 | Enhance - P.L. Zone - Main List | DONE | 2016-09-23 | Don | Dan
07 | Enhance - P.L. Zone - Create new P.L. | DONE | 2016-09-23 | Don | Dan
08 | Enhance - Product - Create new Product | DONE | 2016-09-23 | Thinh | Dan
Activity # | Description | Status | Due Date | Person in Charge | Reviewer | PiC Comment | Feedback
01 | Training - Introduce AngularJS to An | Done |  | Phuong
02 | Training - Introduce ERP Project to An | Done |  | Phuong
PLANNED NEXT SPRINT
ACTIVITY/TASKS # | Description | Due Date | PiC | Comment
01 | P.L. Factory - Create by Copy | 2016-09-26 | Thinh
02 | P.L. Zone - Create by Copy | 2016-09-26 | Don
03 | Pattern - Enhance Main Screen | 2016-09-30 | Don
04 | Pattern - Enhance Detail Screen | 2016-09-30 | Don
05 | Pattern - Enhance Pattern's Part | 2016-09-30 | Don
06 | Pattern - Enhance Pattern's Variation | 2016-09-30 | Thinh
07 | Pattern - Enhance Pattern's Comment | 2016-09-30 | Thinh
08 | Project - Enhance Project's Comment | 2016-09-30 | Thinh
09 | Admin - Fixbug Edit Agent, Zone, Customer | 2016-09-30 | An

## Milestones
Index | Milestone | Due Date | Items
1 | Phase 1 | 2016-09-30 | 1. Admin 2 Costing 3. Price List Factory 4 Price List Zone 5. Project 6. Product
2 | Phase 2 | 2016-10-31 | 1. Order
3 | Phase 3 | 2016-12-30 | General functions
Export data to Excel/PDF - Price List Factory
Export data to Excel/PDF - Price List Zone
Export data to Excel/PDF - Project
Product
Product List - Adding Contract Information
Product Detail - Adding Comment Information
Product List - Export Data to Excel / PDF
Order
Order List - Expor data to Excel/PDF
Add Product - Enhance Procedure to add Product to Order
Order Detail - Enhance Procedure to show product list
Order Detail - Export Product List data to Excel / PDF
Shipment
Basic Data
Shipment Type - CRUD
Freight - CRUD
Fowarder - CRUD
Incoterm - CRUD
Type of Box - CRUD
Shipment
Shipment List - Show list of Shipment
Shipment List - Export data to Excel/PDF
Creating Shipment
Shipment Detail - Adding order item to shipment - Manual
Shipment Detail - Adding order item to shipment - Scan Barcode
Shipment Detail - Show list of items
Shipment Detail - Export list of items to Excel/PDF
Link delivery information from Shipment to Order
Shipment